## Hoja1
Student | Guadalupe Paulina López Cuevas |  |  |  | Date | 2019-11-29
Project | FINAL INDIVIDUAL PROJECT |  |  |  | Language | Java
Date | Start | Stop | Break time | Actual time | Phase | Comment
2019-11-15 | 7:40 a.m. | 8:30 a.m. | 0 | 50 min | Analysis | Analysis of the project I have to make, and check what methods I will have to use.
2019-11-19 | 7:30 a.m. | 8:30 a.m. | 10 min | 50 min | Draft | Start a draft of the interface on the sudoku board, and how many buttons and textfield I will be using. Also the way they are gonig to be organized.
2019-11-22 | 7:20 a.m. | 8:20 a.m. | 20 min | 40 min | Design | Start making the design of the general program, and start thinking about the class diagram and the methods, attributes, classes and packages I will be using for the project.
2019-11-22 | 8:30 p.m. | 10:30 p.m. | 20 min | 1 hora y 40 min | Design | Making the class diagram, the package diagram and the analysis of the relation between the classes and the packages.
2019-11-23 | 8:00 p.m. | 10:00 p.m. | 30 min | 1 hora y 30 min | Implement | Start implementing and creating the classes of menu, level menu and game interface. With buttons, textfield, and instructions.
2019-11-24 | 9:00 p.m. | 10:00 p.m. | 10 min | 50 min | Implement | Start codding the classes of menu, level menu and game interface,and the methods of each button and textfield.
2019-11-25 | 7:20 a.m. | 8:20 a.m. | 10 min | 50 min | Implement | Start codding the classes and methods of the logic of the game. Search the three sudokus to implement three levels.
2019-11-26 | 7:10 a.m. | 10:00 a.m. | 20 min | 2 horas y 30 min | Correcting | Correct the errors of the logic of one of the levels of the game. To check if the logic is good implement.
2019-11-27 | 7:00 p.m. | 8:00 p.m. | 10 min | 50 min | Correcting and compiling | Correcting the errors, searching on internet how to use sertain methods or how to implement them.
2019-11-28 | 11:00 a.m. | 3:00 p.m. | 0 | 4 horas | Correcting and making logic | Write the logic of each level with different sudokus and values in the methods.
2019-11-28 | 7:10 p.m. | 11:30 p.m. | 20 min | 4 horas | Correcting logic compile and fix the aesthetic design | Correcting the wrong implemnetation of oop concepts and separing each level in different interfaces but sahrinng the same logic. Make the game like nice, last check of compiling and finish the time log.
[5 empty] | Total | 18 horas y 60 minutos